Individual Work

CO4830 IT Project Management
Assignment – 1

Submitted by

Manoj M. Chalode
# 1. Introduction
This report consists of an individual work completed by referring the given scenario. The scenario covers up a web based order handling service which is intended to sell leather belts online. This web site will be owned by “Lizzie’s Leather Belts” company. They have given the contract to build this web site to a software development consultancy named “True Concepts”. The intention of this project is to expand the leather belt business by making the products available to the general public online, preferably within 3 months.

The report includes following points which were taken into the consideration for evaluation -
- Stakeholder analysis
- Requirements gathering
- Project life-cycle
- Scheduling
The evaluation is all about discussing the choices made to select the most suitable options for the project and how these options will help the project in achieving the final goal. Apart from it, potential alternative approaches are also discussed which could have been used.
At last but not the least, report focuses on few strategy oriented points like team management, project management & potential professional and legal issues.
# 2. Stakeholder analysis
According to few review reports (Yang, R.J., 2014; Missonier, S. et al. 2014), the stakeholders play an important role in decision-making processes. The analysis provides information about all the potential groups of stakeholders which can impact the projects and their success.

Stakeholder analysis can be done using various methods. These methods use different parameters to set the stakeholders' position with respect to the project. “Construction stakeholder management” book explains a traditional stakeholder analysis (Bourne, L. et al. 2010). Usually, a two dimensional matrix is used to map stakeholders to appropriate groups. This is elaborated in fig 1.

### Figure 1: Traditional stakeholder mapping

The book also enlists some of the widely used dimensions to perform the mapping like power, support, influence, interest, attitude.
## Evaluation
The reason behind choosing power/interest grid for stakeholder prioritization is the dimensions which are being used by this method. The article written by (Ackermann, F. et al. 2011) explains how this grid which uses power & interest as to of its dimensions, is proven to be efficient. The following image clarifies this point.
### Figure 2: Outline stakeholder power-interest grid

In the above figure, it is clearly visible that more the interest or power of a stakeholder closer will be the stakeholder to the system and vice a versa. This relation makes it easier to divide the potential stakeholders into different groups and enables to determine their impact on the system. Stakeholders can then be categorized in different roles by using the ‘Onion’ model technique.
# References

Yang, R.J., 2014. An investigation of stakeholder analysis in urban development projects: Empirical or rationalistic perspectives. International Journal of Project Management, 32(5), pp.838-849.

Missonier, S. and Loufrani-Fedida, S., 2014. Stakeholder analysis and engagement in projects: From stakeholder relational perspective to stakeholder relational ontology. International Journal of Project Management, 32(7), pp.1108-1122.

Bourne, L. and Weaver, P., 2010. Mapping stakeholders. Construction stakeholder management, pp.99-120.

Ackermann, F. and Eden, C., 2011. Strategic management of stakeholders: Theory and practice. Long range planning, 44(3), pp.179-196.

# Images

No.	Title	Source / Reference
Figure 1	Traditional stakeholder mapping	Bourne, L. and Weaver, P., 2010. Mapping stakeholders. Construction stakeholder management, pp.99-120. (book reference)
Figure 2	Outline stakeholder power-interest grid	http://www.sciencedirect.com/science/article/pii/S0024630110000452